## risks
risk_number | risk_name | risk_description | risk_impact | risk_probability
1 | 13. Pod degradation | Excessive degradation of primary packaging during supply chain or in the machine.
5 | 62B. Connected Machine
6 | 20. Clean Cut | Clean cut not aesthetically accepted.
7 | 35. OID digital printing | Delay due to inline digital printing of the code on the capsule
8 | 36. Tech Lead | No global technical / manufacturing lead within project.
9 | 37. Line Single Source | Single source on F&S line puts risk on project timeline and ramp capacity.
10 | 38. FTO Illy | Illy patent on compostable materials
11 | 40. Mach Supplier | Supplier selection process of machine producer should consider the NDG portfolio, not only Group portfolio.
12 | 41. Confidentiality | Challenge to keep confidentiality on the full project with all internal / external stakeholders involved.
13 | 42. R&D mod | R&D module not on time, impact on product validation with consumers
14 | 43. Mat Aging | Aging of materials during storage, shelf-life on system performance.
15 | 44. FTO OID | Code / OID (key element of project).
16 | 45. FTO Doppio | Doppio
17 | 39B. 1size Sustainability | Is there ONE fit ALL packaging solution for EUR / AMS / JP in terms of sustainable waste management / strategy ? (F. Doléac)
18 | 74B. Compatibles
19 | 75B. Early competition
20 | 76B. Competition landscape
21 | 77B. IP Cold Brew
22 | 78B. One single launch (II)
23 | 79B. Short launch dates
24 | 83B. Multi-served
25 | 84B. NGOs
26 | 85B. Serving size
27 | 86B. Venus Brand
28 | 87B. Product range
29 | 88B. Holistic sustainability
30 | 89B. Paper availability
31 | 90B. SKUs quantity
32 | 91B. Sustainability design
33 | 92B. Sourcing
34 | 93B. Data Management
35 | 94B. Cannibalization
36 | 102B. Pod bin | Pod bin capacity too small
37 | 48. FTO Concave
38 | 06. Inflated Pod | Inflated pod not fitting the machine / system performance | 2 | 2
39 | 14. Temporary Materials | Food Safety lead-times to long to continue to allow material changes in the industrialisation phase. | 1 | 1
40 | 07. Temp Control | New feature - Temperature Control - not meeting performance requirements / specs (HACCP issue). | 1 | 1
41 | 25. Machine Mat | Materials selection not according to the global compliance requirements and testing. | 1 | 1
42 | 53. Rychiger Exhibit A | Delay PO for Exhibit A Rychiger | 1 | 1
43 | 81B. Machine Customization |  | 2 | 2
44 | 82B. Machine DTC |  | 1 | 1
45 | 02. Leaking Pod (PLA) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
46 | 15. In cup Q | Unable to reach 60/40 for some products | 2 | 2
47 | 24. Hacking directly firmware | Hacking machine firmware | 4 | 4
48 | 111. Hacking wifi | Hacking machine firmware via wifi | 4 | 4
49 | 29. Line Delays | Delays in manufacturing line development due to new technologies and late decision making process | 4 | 4
50 | 34. Paper Sustainable? | Is paper accepted as sustainable packaging material (e.g. deforestation? water usage?); PLA competition with food. | 4 | 4
51 | 58B. Material evolutions |  | 4 | 4
52 | 64B. Machine late design changes |  | 4 | 4
53 | 66B. Product Personalisation |  | 4 | 4
54 | 67B. Just another machine |  | 4 | 4
55 | 68B. Packaging single source |  | 4 | 4
56 | 69B. One single launch |  | 4 | 4
57 | 70B. Consumer Preference |  | 4 | 4
58 | 71B. Sustainability Perception |  | 4 | 4
59 | 09. Pod ink - FS legislation change | A future change in Ink food safety legislation may make OID inks not usable. | 4 | 4
60 | 04. HC Availability | Availability of industrial compostable accepted materials (pod, pouch). | 1 | 1
61 | 52. 2nd Pack not printable | Secondary Pack Material not ready to receive ink | 1 | 1
62 | 80B. Machine COGS | Today COGS of expert is higher than target | 3 | 3
63 | 33. Tea Pod Mat | Tea pod materials not identified within project time available for launch in 2021. | 2 | 2
64 | 101. New FCM Japan | Potential risk of non-compliant FCM in Japan. | 2 | 2
65 | 11. Unique FS Legislation | Risk that different packagings solutions are required | 2 | 2
66 | 16. Pack Batch Variation | Non-consistent behaviour of paper packaging over different batches. | 3 | 3
67 | 108. Rework | Recipe rework | 2 | 2
68 | 72B. Packaging quantities | Relevance of VENUS quantities of producing needed quantities of packaging vs. Paper industry. | 3 | 3
69 | 18. HC readiness | HC materials readiness | 2 | 2
70 | 21. Commissioning delays | Delays during product commissioning phase. | 2 | 2
71 | 22. Degassing | No clear definition of degassing time (based on lab scale data) on time to develop the upstream. | 2 | 2
72 | 55B. Volume forecast |  | 2 | 2
73 | 73B. ONE Nestlé Sys |  | 2 | 2
74 | 100. Leaking Pod (Ecovio) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
75 | 08. Pod FS reverse printing | Risk that pod ink is not food safety approved for the launch in 2021. | 4 | 4
76 | 17. Industrial Sealing | Loss of barrier related with sealing quality fluctuation during production. | 4 | 4
77 | 23. PP late | Risk that Pyramid plate is not designed on time for the Machine FOT. | 4 | 4
78 | 27. FTO Compostable Pack | FTO Lavazza Patent on Compostable Package with specific puncture resistance of the barrier. | 4 | 4
79 | 28. FTO Multilayer | FTO Lavazza Patent on symmetric multilayer. | 2 | 2
80 | 30. HC Pack Cost | HC Primary packaging cost not meeting business case. | 3 | 3
81 | 31. DTPs | Unable to reach expected Nestlé internal compliance (end-cup quality, DTPs). | 4 | 4
82 | 32. General Delays | Delays in delivering technical milestones (go to development, go to industrialization) due to change in scope, complexity of machine, etc. | 3 | 3
83 | 56B. Globe | Globe make to order / Digital Printing | 2 | 2
84 | 59B. Ban of Capsules |  | 4 | 4
85 | 60B. High Pod Production Cost |  | 4 | 4
86 | 63B. Machine App Security
87 | 65B. Machine single source
88 | 10. Pod FS in-line printing | Risk that pod will not be food safe when printed directly on the paper. | 2 | 2
89 | 105B. Pod acceptance at Composters | No acceptance of compostable materials by EoL local players. | 2 | 2
90 | 54. OTR tests bottleneck | Bottleneck OTR tests | 2 | 2
91 | 100B. Traceability | Traceability requirements arriving too late to be implemented in OID.
92 | 19. EOL 2nd Pack | No acceptance of recyclable materials by EoL local players. | 3 | 3
93 | 49. Pierced Secondary Pack | Flow wrap damaged due to piercing from inside or outside | 3 | 3
94 | 50. FTO Coffee Tablet | EP 2 154 987 B1 - coffee tablet (JDE)
95 | 51. Light impact | Light impact on pod shelf life | 3 | 3
96 | 47. FTO 0 Power | FTO Machine Zero Power
97 | 01. Shelf Life | Combined Primary + Secondary shelf life less than the brief target of 12 months. | 3 | 3
98 | 05. Inflated Secondary Pack | Bag leaks when airfreighted | 3 | 3
99 | 12. OID failure | OID code reading failure | 4 | 4
100 | 03. FTO Eurotab
101 | 46. Bulking | Pod doesn't resist bulking
102 | 95B. DTC earlier
103 | 96B. Ban portioned products
104 | 97B. Asian production
105 | 98B. Data Management (II)
106 | 99B. Hyper segmentation
107 | 109B. Cannibalisation (II)
108 | 101B. Impact G1
109 | 106B. Special T
110 | 103B. Logistic complexity
111 | 100. Line Design Late | Pod industrial line : not available the final design of the line nor validated the forming process
112 | 104B. EoL
113 | 110B. HPPSR | Hybrid high pressure steam roasting
114 | 112. Machine recyclable material | Opportunity to increase the amount of recycled material in the machine
115 | 113. Soft tool delay | Delay in obtaining opex for placing a PO for Machine soft tools
116 | 114. Local origins | Use of local origins could reduce cost
117 | 115. Compaction differences | Risk that 60/40 and other important project validations are not representative of final technology. | 4 | 4
118 | 116. FTO PP design | FTO assessment to be done with new pyramid plate design | 3 | 3
119 | 117. Delamination HC top |  | 4 | 4
120 | 118. 2nd Box DTC | Have a an alternative 2nd Pack (Box) targeting e-commerce sales.
121 | 119. 2D code | Bridging solution until having OID bringing supply chain traceability (target 2022)
122 | 120. OID with traceability | Implementing Supply Chain traceability into the OID coding
123 | 121. Customs delays AMS (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Brasil)
124 | 122. Customs delays EMENA (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Girona)
125 | 123. Tax environment Mercosur | Import duties / tax environment impact selection of location for local production in Mercosur. | 3 | 3
126 | 124. FTO IoT | IoT patent?
127 | 125. Localisation Mach Prod | Local assembly of machines
128 | 126. FCM compliance Pack BR - G-polymer | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4
129 | 127. Local readiness conn.machine | Put setup in place to leverage IoT data.
130 | 128. Airfreght | Occurrence of unexpected defects on the product / packaging during airfreight
131 | 129. FCM compliance Pack BR - cellophane | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4

## actions
action_number | risk_number | action_description | action_responsible | action_deadline
1000 | 1 | Material selection based on experience from NDG Gen1 for Global compliance | D.Vuagniaux
1001 | 1 | 1.Leaking action plan: - identify why and where leakage, breakage - select optimal ultra sonic sealing tools - ensure 5k doesn't damage bottom - identify optimal settings for industrial top membrane to minimize Ray ban effect - identify optimal ultra sonic sealing parameters (20/30kHz) - anticipate potential structures with higher thickness of sealant layers - assess adequation of PLA and sandwich structures compared to other materials and structures | F.Marville
1002 | 1 | 1. Basic design credit to be provided by R&D and later transferred to the market | J.Favre
1003 | 1 | 2. Industrial Capex to be requested | P.DeSantis
1004 | 1 | 3. Have project brief and line URS available on time | J.Favre
1005 | 1 | 1. assess influence of light on pod raw material | C.Donier
1006 | 1 | 2. check historical info on influence of light on product (coffee) | J.Pacault
1007 | 1 | 2. Better understand mechanical behaviour of different structures & limits with system | F.Marville
1008 | 1 | 1. Cold brew cross contamination assessment | F.Pereira
1009 | 1 | 1. Secure validation of consumer test with with hand-made samples. | J.Pacault
1010 | 1 | Refer legal document, action preparing opposition being prepared. | S.Odet
1011 | 1 | Meeting with Corporate Supply Chain and Globe Business Solution to define mitigation action. | Y.Pottier
1012 | 1 | Current shelf life figures with Secondary Pack still theoretical, assessment of real shelf life with Secondary Pack to be initiated with physical samples asap. Repeat tests as first round is not conclusive due to doubts about pack tightness. | J.Pacault
1013 | 1 | Confirmation ok for Swiss legislation | B.Icli
1014 | 1 | Clarify what are the OID requirements for launch (trade-off between traceability and Product Development). | A.Noth
1015 | 1 | Present to GBU options on code areas allocation among product, machine and traceability in order to freeze the OID code design for FOT (01.01.2020) | A.Noth
1016 | 1 | Testing initiated, EU and FDA ok but Japan and Mercosur results not cleared yet. Feedback expected by year end 2019. | B.Icli
1017 | 1 | Define clear in cup quality standards for all product to feed pyramid plate design | A.Trullard
1018 | 1 | Optimise sealing strength - produce samples to assess current sealing strength. Assess of contribution of flushing in Secondary Pack. | C.Monin
1019 | 1 | Choose machine mould cavities (1 vs multi-cavities) before go to indus | C.Meire
1020 | 1 | 2. Verify if Nespresso Pro prior use is confirmed. 3. Check if there is legal validly (prior art). | S.Odet
1021 | 1 | Hacking: Security assessment + hardware chip to be re-evaluated following Wi-Fi integration in the scope | S.Siddiqi
1022 | 1 | Obtain reliable quotes | W.Lee
1023 | 1 | To avoid scope changes agree on a brief - on-going brief preparation in dedicated recurring meetings STC-GBU. Outcome will be used to gate the project and formalise decisions. | P.Mul
1024 | 1 | Based on material composition validate if it could ever be categorised as plastic capsule | S.Kulhanek
1025 | 1 | 1) Set the security level with DSU 2) Make sure this is a priority for DSU | D.Elshaal
1026 | 1 | Visualize Machine Producer/EF workload (dedicated project team on the OEM). | P.Melo
1027 | 1 | 2nd supplier development re-initiated for alternative solution, but will not be able to be ready for the launch, only for back up plan. | E.Mayer
1028 | 1 | 1. Clarify how to validate Compostability worldwide 2. Secure materials for pre-assessment and certification 3. Obtain certification | D.Nordqvist
1029 | 1 | - Provide due diligence to the Recycling Partners - Nestlé guideline to be updated for the NDG Launch Markets | R.Witik
1030 | 1 | Identify Root Causes for delamination. The tie layer has been identified as the root cause for delamination. | C.Magri
1031 | 1 | Calibrate the STC compaction with Festo (D.Rosser from Festo to come Monday for Calibration). Request the “How does it work?” to Festo and make the parallel with IMA Techno | J.Favre
1032 | 1 | Issue draft shelf life test protocol and share it with the team for review before test campain kick off. | J.Pacault
1033 | 1 | Contact PTC to try to establish a predictive model of the potential DTPs in different Venus recipes (and obtain latest know how on the domain). | J.Pacault
1034 | 1 | Monitoring of DTPs integrated in the Product Screening activities and system design | J.Pacault
1035 | 1 | Workshop on internal internal alignment on Business model. | D.Elshaal
1036 | 1 | T2T with Wik management (including Macedonia setup). | M.Lohner
1037 | 1 | Extra measure of machine reading OID before commanding brew. | E.Gabbud
1038 | 1 | Assessment of potential compaction differences between the different production tools - Rychiger, IMA and STC and related influence on In cup quality and System Performance. | F.Marville
1039 | 1 | Clarify the EoL requirements for Mercosur markets | D.Nordqvist
1040 | 1 | Investigate localisation possibilities for Venus laminate structures in AMS -> start by screening potential suppliers | W.Lee
1041 | 1 | Understand how the pod paper laminate is classified (Brasil as lead market) - e.g: paper based, plastic laminate with paper. | Y.Pottier
1042 | 1 | Provide Packaging team test condition for airfreight simulation test | Y.Pottier
1043 | 1 | Optimise sealing parameters and adhesive / tie layers that minimise delamination | N.Grès
1044 | 1 | Define the count in the tertiary pack. | P.Wouters
1045 | 1 | Optimise material thickness -> assess technical feasibility in parallel of the selected materials for launch. | C.Magri
1046 | 1 | Consolidate DTPs levels for current PGT recipes and of HC materials. | J.Pacault
1047 | 1 | Assess possibility replacement of G-Polymer by EVOH (non compostable but could still be accepted if smaller than 10% weight of the total) | D.Nordqvist
1048 | 1 | Establish clear specification paper base materials and storage conditions. | C.Magri
1049 | 1 | Evaluate alternative Secondary Pack with better moisture barrier performance for Launch, with a trade off on recyclability performance | O.Martin
1050 | 1 | Assess optimal sealing parameters and inline sealing monitoring | B.Kunzle
1051 | 1 | Actions on electronic on going Actions on Chrome replacement ongoing | D. Vuagniaux
1052 | 1 | Ask composters in the markets / EU Environment Commissions if the Venus Pod is accepted in the composting IC. | S.Kulhanek
1053 | 1 | Investigate replacing virgin aluminium with recycled aluminium. | D. Vuagniaux
1054 | 1 | As mitigation plan - investigate replacement of top membrane plastic layer by an alternative material and the removal of barrier from primary pack and list technical consequences / constraints. | P.Mul
1055 | 1 | Share with the Venus Brazilian team this food safety risk and request local team to leverage local network in getting the g-polymer in the positive list on time. | P.Wouters
1056 | 1 | Have top membrane with OID with final printing quality to feed machine Life Cycle Tests. | C.Magri
1057 | 1 | Clarify OID failure rate acceptable level (use benchmarks from Vertuo and other consumer related experience criteria, liase with business for Quality expectations) | A.Noth
1058 | 1 | Perform many printing trials and suitable material choice to achieve excellent reliability. | C.Magri
1059 | 1 | Screening of available extraction parameters for customisation and potential impacts on DTPs. | J.Pacault
1060 | 1 | Assess expected OID failure rate based on FOT LCT test | A.Noth
1061 | 1 | 5. Transport tests with OID in the centre to be initiated | A.Noth
1062 | 1 | Look for inks that are food-safe on the long term. | F.Doléac
1063 | 1 | 1. Evaluate food safety of Digital printing technology when applied to pod. 2. Evaluate if Nestlé would establish a DoC internally even if suppliers are not providing it. 3. Look for inks that are food formulation and technically adapted to laminate printing. | F.Doléac
1064 | 1 | Obtain certification | D.Nordqvist
1065 | 1 | Reassess with the potential differences Rychiger-IMA line-Lab,with pods with the final pyramid plate, with 12.2ml for S, cavities in the IMA line. | N.Dogan
1066 | 1 | 1. Full assess if Venus is in or out of the patent needed (and how much). | J.Pacault
1067 | 1 | Assess forming of alternative Sec Pack materials | C.Monin
1068 | 1 | 1. Assessment of the degassing impacts (DOE) and correlation with altitude. | J.Pacault
1069 | 1 | 2. Evaluate contribution of Vacuum technology to fix the problem. | J.Pacault
1070 | 1 | 3. Assessment of US sealing performance for Industrial Compostable (material - anvil couple) + improvement potential. | N.Grès
1071 | 1 | 4. Evaluate other mitigation actions (concave bottom, grinder temperature, packaging with higher resistance,...) | J.Pacault
1072 | 1 | 5. Open pod: evaluate the possibility of having full barrier on the secondary pack to remove it from the pod. | C.Monin
1073 | 1 | Tasting with HC materials (tropical and standard) after 3 months shelf life | J.Pacault
1074 | 1 | No action expected. | D.Elshaal
1075 | 1 | 1. Decision taken to launch with Industrial Compostable pod / or Home compostable when and if available. 2. Continue with BASF development and Mondi lamination | F.Doléac
1076 | 1 | 1. Inform and ask the FCM suppliers to submit the request for the addition of their missing substances to the Japanese authorities. 2. Further actions to be defined (if necessary) once the final Positive List is published (expected Dec.2019). 3. Business to rate impact if Japan sales not possible | B.Icli
1077 | 1 | Ch. Monin / F. Diaz: work on this concept to have more robust comparison.
1078 | 1 | P. Mul: Make composting trials with lead materials to proof the acceptance by composters. Y. Pottiers
1079 | 1 | 4. Machine Lifecycle tests planned
1080 | 1 | 1. Prepare communication for markets where infrastructure is missing (tbc)
1081 | 1 | Filter out showstoppers -> showstoppers are top risks in this risk management file. All technical risks in the project are centralised in this file and reviewed weekly. Top risks are then reported in SteerCOs.
1082 | 1 | Appeal from JDE in progress, appeal being monitored.JDE may confirm limitation (70-120), and symmetry.
F.Marville appointed as Technical Coordinator for the Pod Project.
1. Identify second supplier where Nestlé would have higher priority;
Patent is now limited only PHA.
Risk moved to the Sachet file according to scope change of moving tea to sachet.
Development and Industrial suppliers selected - Helbling, Wik.
1. OID code moved to the centre of the Pod and groove moved to underneath the rim thus FTO is ok. Patent pending - becomes an opportunity.
1. Clarify/define raw materials shelf life targets with the support of the Pack and Supply Chain teams.
2. File patent application
1. Specify detailed bulking requirements in factory environment and do related technical validation tests
Confirm if patent still valid due to non payment of renewal fees.
1. Plan SOP with DTC.
1. File patent application
1. Very quickly, organize ourselves internally (GBU & STC) to define GBU Lead & STC Lead (with clear briefs) 2. Lessons learnt (Esperta, Barista, Genio-San) 3. Plan functionalities workshop in Feb. 2019
1. Evaluate possibility to overdesign the machine to make it compatible with different material specs. 2. Obtain a initial IC certification on the HC material in order to be reduce the composting validation time 3. G. Demaurex: Modify the opening of the POD by a positive opening (e.g. mechanical) 4. When legislation changes design new material meeting system specs
1. Include in RFP brief.
1. Identify OEM by mid March to ensure alignment of DFM / DFA analysis prior to machine design freeze 2. no major changes in project scope / brief nor functionalities after Design freeze (Go to Dev.)
Define back end configuration for online platform with Edouard
E. Seid F. Doléac P. Wouters / A. Marchesi / D. Elshaal: Keep doing homework well…! Get external help for this one.
P. Mul: Align Nestle senior management via SC's.
Y. Pottiers: Date of 1 April 2021 to be approved (SOP); use R&D module
Build clear action plan with WIK before supplier selection, in case we want to go with them
Checking IP in connection to IoT connectivity
Check feasibility of modifying supply chain in tropical countries with 8 -11 months shelf life and related cost impacts.
Define Primary pod bulking method to fulfill shelf life and transport requirements.

## users
user_name | user_department
I.Capell | Engineering
P.Mul | LTM
J.Ramalho | Venus
J.Favre | Engineering
L.Voina | Regulatory
J.Pacault | Product
S.Chafil | Product
F.Neves | Quality
J.Petry | Quality
C.Meire | SupplyChain
B.Pfister | Marketing
P.Wouters | Marketing