## risks
risk_number | risk_name | risk_description | risk_impact | risk_probability
1 | Short circuit | Due to wrong assembly a short circuit triggers a fire in the engine | 2 | 4
2 | Battery leakage | During the warranty period a leakage of the batery occurs during travel leading to car stop | 3 | 2
3 | Rusty terminals | If car left on charge for an entire week in tropical countries | 2 | 4

## actions
action_number | risk_number | action_description | action_responsible | action_deadline
1000 | 1 | Establish Standard Operation procedure for cable mounting | John Smith | 20200210
1001 | 1 | Establish Test Method for cable connection | Paul Warren | 20200212
1002 | 2 | Refine authonomy calculation now including effects of temperature | Angela Python | 20201220
1003 | 2 | Present proposal to the Steering Committee for upgrade to generation 3 in all mid range platforms | Jessica Morris | 20201223