## risks
risk_number | risk_name | risk_description | risk_impact | risk_probability
1 | Packaging materials not tight |  | 1 | 4
2 | New risk |  | 1 | 1
5 | 62B. Connected Machine
6 | 20. Clean Cut | Clean cut not aesthetically accepted.
7 | 35. OID digital printing | Delay due to inline digital printing of the code on the capsule
8 | 36. Tech Lead | No global technical / manufacturing lead within project.
9 | 37. Line Single Source | Single source on F&S line puts risk on project timeline and ramp capacity.
10 | 38. FTO Illy | Illy patent on compostable materials
11 | 40. Mach Supplier | Supplier selection process of machine producer should consider the NDG portfolio, not only Group portfolio.
12 | 41. Confidentiality | Challenge to keep confidentiality on the full project with all internal / external stakeholders involved.
13 | 42. R&D mod | R&D module not on time, impact on product validation with consumers
14 | 43. Mat Aging | Aging of materials during storage, shelf-life on system performance.
15 | 44. FTO OID | Code / OID (key element of project).
16 | 45. FTO Doppio | Doppio
17 | 39B. 1size Sustainability | Is there ONE fit ALL packaging solution for EUR / AMS / JP in terms of sustainable waste management / strategy ? (F. Doléac)
18 | 74B. Compatibles
19 | 75B. Early competition
20 | 76B. Competition landscape
21 | 77B. IP Cold Brew
22 | 78B. One single launch (II)
23 | 79B. Short launch dates
24 | 83B. Multi-served
25 | 84B. NGOs
26 | 85B. Serving size
27 | 86B. Venus Brand
28 | 87B. Product range
29 | 88B. Holistic sustainability
30 | 89B. Paper availability
31 | 90B. SKUs quantity
32 | 91B. Sustainability design
33 | 92B. Sourcing
34 | 93B. Data Management
35 | 94B. Cannibalization
36 | 102B. Pod bin | Pod bin capacity too small
37 | 48. FTO Concave
38 | 06. Inflated Pod | Inflated pod not fitting the machine / system performance | 2 | 2
39 | 14. Temporary Materials | Food Safety lead-times to long to continue to allow material changes in the industrialisation phase. | 1 | 1
40 | 07. Temp Control | New feature - Temperature Control - not meeting performance requirements / specs (HACCP issue). | 1 | 1
41 | 25. Machine Mat | Materials selection not according to the global compliance requirements and testing. | 1 | 1
42 | 53. Rychiger Exhibit A | Delay PO for Exhibit A Rychiger | 1 | 1
43 | 81B. Machine Customization |  | 2 | 2
44 | 82B. Machine DTC |  | 1 | 1
45 | 02. Leaking Pod (PLA) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
46 | 15. In cup Q | Unable to reach 60/40 for some products | 2 | 2
47 | 24. Hacking directly firmware | Hacking machine firmware | 4 | 4
48 | 111. Hacking wifi | Hacking machine firmware via wifi | 4 | 4
49 | 29. Line Delays | Delays in manufacturing line development due to new technologies and late decision making process | 4 | 4
50 | 34. Paper Sustainable? | Is paper accepted as sustainable packaging material (e.g. deforestation? water usage?); PLA competition with food. | 4 | 4
51 | 58B. Material evolutions |  | 4 | 4
52 | 64B. Machine late design changes |  | 4 | 4
53 | 66B. Product Personalisation |  | 4 | 4
54 | 67B. Just another machine |  | 4 | 4
55 | 68B. Packaging single source |  | 4 | 4
56 | 69B. One single launch |  | 4 | 4
57 | 70B. Consumer Preference |  | 4 | 4
58 | 71B. Sustainability Perception |  | 4 | 4
59 | 09. Pod ink - FS legislation change | A future change in Ink food safety legislation may make OID inks not usable. | 4 | 4
60 | 04. HC Availability | Availability of industrial compostable accepted materials (pod, pouch). | 1 | 1
61 | 52. 2nd Pack not printable | Secondary Pack Material not ready to receive ink | 1 | 1
62 | 80B. Machine COGS | Today COGS of expert is higher than target | 3 | 3
63 | 33. Tea Pod Mat | Tea pod materials not identified within project time available for launch in 2021. | 2 | 2
64 | 101. New FCM Japan | Potential risk of non-compliant FCM in Japan. | 2 | 2
65 | 11. Unique FS Legislation | Risk that different packagings solutions are required | 2 | 2
66 | 16. Pack Batch Variation | Non-consistent behaviour of paper packaging over different batches. | 3 | 3
67 | 108. Rework | Recipe rework | 2 | 2
68 | 72B. Packaging quantities | Relevance of VENUS quantities of producing needed quantities of packaging vs. Paper industry. | 3 | 3
69 | 18. HC readiness | HC materials readiness | 2 | 2
70 | 21. Commissioning delays | Delays during product commissioning phase. | 2 | 2
71 | 22. Degassing | No clear definition of degassing time (based on lab scale data) on time to develop the upstream. | 2 | 2
72 | 55B. Volume forecast |  | 2 | 2
73 | 73B. ONE Nestlé Sys |  | 2 | 2
74 | 100. Leaking Pod (Ecovio) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
75 | 08. Pod FS reverse printing | Risk that pod ink is not food safety approved for the launch in 2021. | 4 | 4
76 | 17. Industrial Sealing | Loss of barrier related with sealing quality fluctuation during production. | 4 | 4
77 | 23. PP late | Risk that Pyramid plate is not designed on time for the Machine FOT. | 4 | 4
78 | 27. FTO Compostable Pack | FTO Lavazza Patent on Compostable Package with specific puncture resistance of the barrier. | 4 | 4
79 | 28. FTO Multilayer | FTO Lavazza Patent on symmetric multilayer. | 2 | 2
80 | 30. HC Pack Cost | HC Primary packaging cost not meeting business case. | 3 | 3
81 | 31. DTPs | Unable to reach expected Nestlé internal compliance (end-cup quality, DTPs). | 4 | 4
82 | 32. General Delays | Delays in delivering technical milestones (go to development, go to industrialization) due to change in scope, complexity of machine, etc. | 3 | 3
83 | 56B. Globe | Globe make to order / Digital Printing | 2 | 2
84 | 59B. Ban of Capsules |  | 4 | 4
85 | 60B. High Pod Production Cost |  | 4 | 4
86 | 63B. Machine App Security
87 | 65B. Machine single source
88 | 10. Pod FS in-line printing | Risk that pod will not be food safe when printed directly on the paper. | 2 | 2
89 | 105B. Pod acceptance at Composters | No acceptance of compostable materials by EoL local players. | 2 | 2
90 | 54. OTR tests bottleneck | Bottleneck OTR tests | 2 | 2
91 | 100B. Traceability | Traceability requirements arriving too late to be implemented in OID.
92 | 19. EOL 2nd Pack | No acceptance of recyclable materials by EoL local players. | 3 | 3
93 | 49. Pierced Secondary Pack | Flow wrap damaged due to piercing from inside or outside | 3 | 3
94 | 50. FTO Coffee Tablet | EP 2 154 987 B1 - coffee tablet (JDE)
95 | 51. Light impact | Light impact on pod shelf life | 3 | 3
96 | 47. FTO 0 Power | FTO Machine Zero Power
97 | 01. Shelf Life | Combined Primary + Secondary shelf life less than the brief target of 12 months. | 3 | 3
98 | 05. Inflated Secondary Pack | Bag leaks when airfreighted | 3 | 3
99 | 12. OID failure | OID code reading failure | 4 | 4
100 | 03. FTO Eurotab
101 | 46. Bulking | Pod doesn't resist bulking
102 | 95B. DTC earlier
103 | 96B. Ban portioned products
104 | 97B. Asian production
105 | 98B. Data Management (II)
106 | 99B. Hyper segmentation
107 | 109B. Cannibalisation (II)
108 | 101B. Impact G1
109 | 106B. Special T
110 | 103B. Logistic complexity
111 | 100. Line Design Late | Pod industrial line : not available the final design of the line nor validated the forming process
112 | 104B. EoL
113 | 110B. HPPSR | Hybrid high pressure steam roasting
114 | 112. Machine recyclable material | Opportunity to increase the amount of recycled material in the machine
115 | 113. Soft tool delay | Delay in obtaining opex for placing a PO for Machine soft tools
116 | 114. Local origins | Use of local origins could reduce cost
117 | 115. Compaction differences | Risk that 60/40 and other important project validations are not representative of final technology. | 4 | 4
118 | 116. FTO PP design | FTO assessment to be done with new pyramid plate design | 3 | 3
119 | 117. Delamination HC top |  | 4 | 4
120 | 118. 2nd Box DTC | Have a an alternative 2nd Pack (Box) targeting e-commerce sales.
121 | 119. 2D code | Bridging solution until having OID bringing supply chain traceability (target 2022)
122 | 120. OID with traceability | Implementing Supply Chain traceability into the OID coding
123 | 121. Customs delays AMS (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Brasil)
124 | 122. Customs delays EMENA (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Girona)
125 | 123. Tax environment Mercosur | Import duties / tax environment impact selection of location for local production in Mercosur. | 3 | 3
126 | 124. FTO IoT | IoT patent?
127 | 125. Localisation Mach Prod | Local assembly of machines
128 | 126. FCM compliance Pack BR - G-polymer | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4
129 | 127. Local readiness conn.machine | Put setup in place to leverage IoT data.
130 | 128. Airfreght | Occurrence of unexpected defects on the product / packaging during airfreight
131 | 129. FCM compliance Pack BR - cellophane | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4
144 | Test risk 144 |  | 1 | 2