## Sheet 1
risk_number | risk_name | risk_description | risk_impact | risk_probability
1 | Packaging materials not tight | Because problem in the line test. | 3 | 4
2 | Test risk 2 | Test risk description 2 for download. | 0 | 0
4 |  |  | 0 | 0
5 | Connected Machine | NA | 1 | 1
6 | Clean Cut | Clean cut not aesthetically accepted. | 1 | 1
7 | OID digital printing | Delay due to inline digital printing of the code on the capsule | 1 | 1
9 | 37. Line Single Source | Single source on F&S line puts risk on project timeline and ramp capacity.
10 | 38. FTO Illy | Illy patent on compostable materials
11 | 40. Mach Supplier | Supplier selection process of machine producer should consider the NDG portfolio, not only Group portfolio.
12 | 41. Confidentiality | Challenge to keep confidentiality on the full project with all internal / external stakeholders involved.
13 | 42. R&D mod | R&D module not on time, impact on product validation with consumers
14 | 43. Mat Aging | Aging of materials during storage, shelf-life on system performance.
15 | 44. FTO OID | Code / OID (key element of project).
16 | 45. FTO Doppio | Doppio
17 | 39B. 1size Sustainability | Is there ONE fit ALL packaging solution for EUR / AMS / JP in terms of sustainable waste management / strategy ? (F. Doléac)
18 | 74B. Compatibles
19 | 75B. Early competition
20 | 76B. Competition landscape
21 | 77B. IP Cold Brew
22 | 78B. One single launch (II)
23 | 79B. Short launch dates
24 | 83B. Multi-served
25 | 84B. NGOs
26 | 85B. Serving size
27 | 86B. Venus Brand
28 | 87B. Product range
29 | 88B. Holistic sustainability
30 | 89B. Paper availability
31 | 90B. SKUs quantity
32 | 91B. Sustainability design
33 | 92B. Sourcing
34 | 93B. Data Management
35 | 94B. Cannibalization
36 | 102B. Pod bin | Pod bin capacity too small
37 | 48. FTO Concave
38 | 06. Inflated Pod | Inflated pod not fitting the machine / system performance. Potential impacts: Delamination, loss of tightness, increase of total size making difficult/impossible introduction in the machine. | 2 | 2
39 | 14. Temporary Materials | Food Safety lead-times to long to continue to allow material changes in the industrialisation phase. | 1 | 1
40 | 07. Temp Control | New feature - Temperature Control - not meeting performance requirements / specs (HACCP issue). | 1 | 1
41 | 25. Machine Mat | Materials selection not according to the global compliance requirements and testing. | 1 | 1
42 | 53. Rychiger Exhibit A | Delay PO for Exhibit A Rychiger | 1 | 1
43 | 81B. Machine Customization |  | 2 | 2
44 | 82B. Machine DTC |  | 1 | 1
45 | 02. Leaking Pod (PLA) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
46 | 15. In cup Q | Unable to reach 60/40 for some products | 2 | 2
47 | 24. Hacking directly firmware | Hacking machine firmware | 4 | 4
48 | 111. Hacking wifi | Hacking machine firmware via wifi | 4 | 4
49 | 29. Line Delays | Delays in manufacturing line development due to new technologies and late decision making process | 4 | 4
50 | 34. Paper Sustainable? | Is paper accepted as sustainable packaging material (e.g. deforestation? water usage?); PLA competition with food. | 4 | 4
51 | 58B. Material evolutions |  | 4 | 4
52 | 64B. Machine late design changes |  | 4 | 4
53 | 66B. Product Personalisation |  | 4 | 4
54 | 67B. Just another machine |  | 4 | 4
55 | 68B. Packaging single source |  | 4 | 4
56 | 69B. One single launch |  | 4 | 4
57 | 70B. Consumer Preference |  | 4 | 4
58 | 71B. Sustainability Perception |  | 4 | 4
59 | Pod ink - Food Safety | Risk that pod ink is not food safety approved for the launch in 2021. The current pod concept foreseen for launch is based on a laminate with reverse printing on PLA or cellophane With this concept and the current system design the inks dissolve into coffee during extraction? -> confirm On the other hand the system cannot work without OID. A problem in the Ink food safety would make the system complete non-usable as it is not possible to remove the OID. As the same ink is used for Nespresso professional a validation is expected also for Venus. Currently the only country where legislation is foreseen to change is China (China is on the process of creation ink legislation, pod might become non compliant). Tests for food safety on IC have been stopped (26.05.2020) We have the verification from Mondi that the formulation of both OID ink and marketing ink are ok according to swiss and Nestle requirements. | 4 | 2
60 | 04. HC Availability | Availability of industrial compostable accepted materials (pod, pouch). | 1 | 1
61 | 52. 2nd Pack not printable | Secondary Pack Material not ready to receive ink | 1 | 1
62 | 80B. Machine COGS | Today COGS of expert is higher than target | 3 | 3
63 | 33. Tea Pod Mat | Tea pod materials not identified within project time available for launch in 2021. | 2 | 2
64 | 101. New FCM Japan | Potential risk of non-compliant FCM in Japan. | 2 | 2
65 | 11. Unique FS Legislation | Risk that different packagings solutions are required | 2 | 2
66 | 16. Pack Batch Variation | Non-consistent behaviour of paper packaging over different batches. | 3 | 3
67 | 108. Rework | Recipe rework | 2 | 2
68 | 72B. Packaging quantities | Relevance of VENUS quantities of producing needed quantities of packaging vs. Paper industry. | 3 | 3
69 | 18. HC readiness | HC materials readiness | 2 | 2
70 | 21. Commissioning delays | Delays during product commissioning phase. | 2 | 2
71 | 22. Degassing | No clear definition of degassing time (based on lab scale data) on time to develop the upstream. | 2 | 2
72 | 55B. Volume forecast |  | 2 | 2
73 | 73B. ONE Nestlé Sys |  | 2 | 2
74 | 100. Leaking Pod (Ecovio) | Leaking pods (this relates to the risk of breakage of plastic layer, due to ageing, altitude, external pressure,...) | 4 | 4
75 | 08. Pod FS reverse printing | Risk that pod ink is not food safety approved for the launch in 2021. | 4 | 4
76 | 17. Industrial Sealing | Loss of barrier related with sealing quality fluctuation during production. | 4 | 4
77 | 23. PP late | Risk that Pyramid plate is not designed on time for the Machine FOT. | 4 | 4
78 | 27. FTO Compostable Pack | FTO Lavazza Patent on Compostable Package with specific puncture resistance of the barrier. | 4 | 4
79 | 28. FTO Multilayer | FTO Lavazza Patent on symmetric multilayer. | 2 | 2
80 | 30. HC Pack Cost | HC Primary packaging cost not meeting business case. | 3 | 3
81 | 31. DTPs | Unable to reach expected Nestlé internal compliance (end-cup quality, DTPs). | 4 | 4
82 | 32. General Delays | Delays in delivering technical milestones (go to development, go to industrialization) due to change in scope, complexity of machine, etc. | 3 | 3
83 | 56B. Globe | Globe make to order / Digital Printing | 2 | 2
84 | 59B. Ban of Capsules |  | 4 | 4
85 | 60B. High Pod Production Cost |  | 4 | 4
86 | 63B. Machine App Security
87 | 65B. Machine single source
88 | 10. Pod FS in-line printing | Risk that pod will not be food safe when printed directly on the paper. | 2 | 2
89 | 105B. Pod acceptance at Composters | No acceptance of compostable materials by EoL local players. | 2 | 2
90 | 54. OTR tests bottleneck | Bottleneck OTR tests | 2 | 2
91 | 100B. Traceability | Traceability requirements arriving too late to be implemented in OID.
92 | 19. EOL 2nd Pack | No acceptance of recyclable materials by EoL local players. | 3 | 3
93 | 49. Pierced Secondary Pack | Flow wrap damaged due to piercing from inside or outside | 3 | 3
94 | 50. FTO Coffee Tablet | EP 2 154 987 B1 - coffee tablet (JDE)
95 | 51. Light impact | Light impact on pod shelf life | 3 | 3
96 | 47. FTO 0 Power | FTO Machine Zero Power
97 | Shelf Life | Combined Primary + Secondary shelf life less than the brief target of 12 months. Calculations show that closed shelf life will be >12 month in European conditions and in tropical countries from 8 to 11 months. A final shelf life test with final materials is planned Q1 2020. | 3 | 4
98 | Inflated Secondary Pack | Bag leaks when airfreighted. Bag could open during transport and leak loosing the shelf life, worst case scenario loosing physical integrity and pods falling. To be re-evaluated for Brazil DTC, depending on supply chain it will likely be a lower risk. | 3 | 3
99 | 12. OID failure | OID code reading failure | 4 | 4
100 | 03. FTO Eurotab
101 | 46. Bulking | Pod doesn't resist bulking
102 | 95B. DTC earlier
103 | 96B. Ban portioned products
104 | 97B. Asian production
105 | 98B. Data Management (II)
106 | 99B. Hyper segmentation
107 | 109B. Cannibalisation (II)
108 | 101B. Impact G1
109 | 106B. Special T
110 | 103B. Logistic complexity
111 | 100. Line Design Late | Pod industrial line : not available the final design of the line nor validated the forming process
112 | 104B. EoL
113 | 110B. HPPSR | Hybrid high pressure steam roasting
114 | 112. Machine recyclable material | Opportunity to increase the amount of recycled material in the machine
115 | 113. Soft tool delay | Delay in obtaining opex for placing a PO for Machine soft tools
116 | 114. Local origins | Use of local origins could reduce cost
117 | 115. Compaction differences | Risk that 60/40 and other important project validations are not representative of final technology. | 4 | 4
118 | 116. FTO PP design | FTO assessment to be done with new pyramid plate design | 3 | 3
119 | 117. Delamination HC top |  | 4 | 4
120 | 118. 2nd Box DTC | Have a an alternative 2nd Pack (Box) targeting e-commerce sales.
121 | 119. 2D code | Bridging solution until having OID bringing supply chain traceability (target 2022)
122 | 120. OID with traceability | Implementing Supply Chain traceability into the OID coding
123 | 121. Customs delays AMS (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Brasil)
124 | 122. Customs delays EMENA (Equipment) | Risk of equipment being retained in customs during the transportation (if local manufacturing in Girona)
125 | 123. Tax environment Mercosur | Import duties / tax environment impact selection of location for local production in Mercosur. | 3 | 3
126 | 124. FTO IoT | IoT patent?
127 | 125. Localisation Mach Prod | Local assembly of machines
128 | 126. FCM compliance Pack BR - G-polymer | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4
129 | 127. Local readiness conn.machine | Put setup in place to leverage IoT data.
130 | 128. Airfreght | Occurrence of unexpected defects on the product / packaging during airfreight
131 | 129. FCM compliance Pack BR - cellophane | Risk of late food safety / regulatory approval of packaging materials (and machine) for launch in Brazil | 4 | 4
144 | Test risk 144 |  | 1 | 2